## Sheet1
No. | Discussions | Last Updated
D282 | PAMAC (Cloud Version) | 2023-11-24
Ramakrishnan V - SQL query optimization
D280 | PAMAC (Cloud Version) | 2023-11-23
Ramakrishnan V - Clients Service ID to be configured in the SMS
D289 | PAMAC (Cloud Version) | 2023-11-08
Ramakrishnan V - Support Task
D287 | PAMAC (Cloud Version) | 2023-10-25
(All Members) - Software versions and php info
D270 | PAMAC (Cloud Version) | 2023-09-26
(All Members) - PAMAC Access Rights
My Requirements
No. | Requirements | Last Updated
R126 | PAMAC (Cloud Version) | 2023-10-10
Ramakrishnan V - Auto inactive user in the RES if no any activity done in the last 30 days
R134 | PAMAC (Cloud Version) | 2023-10-05
Ramakrishnan V - Required Auto logout to be set for the INDIA
R137 | PAMAC (Cloud Version) | 2023-10-04
Ramakrishnan V - Image compress size to be increase for the clarity
R123 | PAMAC (Cloud Version) | 2023-08-07
(All Members) - AWS India Check List
Open Projects
Sr No. | Project Name | Start Date | End Date
1 | PAMAC (Cloud Version) | 2013-12-23 | 2023-12-31
Daily Updates
View More
No. | Project Name | Subject | Last Updated
DU1961 | PAMAC (Cloud Version) | Manas Dasgupta | 2023-11-24
Daily report
DU1960 | PAMAC (Cloud Version) | Manas Dasgupta | 2023-11-23
Daily report
DU1959 | PAMAC (Cloud Version) | Manas Dasgupta | 2023-11-22
Daily report
DU1958 | PAMAC (Cloud Version) | Manas Dasgupta | 2023-11-21
Daily report
DU1957 | PAMAC (Cloud Version) | Manas Dasgupta | 2023-11-20
Daily report

## Sheet2
No. | Posting Date | Subject | Status | Action
R1 | 2014-02-19 01:02 | Requirement Analysis Documents | Close
R2 | 2016-05-13 10:25 | FE employee code in pdf report | Close
R3 | 2016-06-03 15:03 | Attached cases to be archived today | Close
R4 | 2016-08-22 19:21 | Data required from Archive to live - 101853177, 101877100 | Close
R5 | 2016-08-31 11:50 | Cases to be temporarily moved - Dubai | Close
R6 | 2016-09-12 13:27 | Usable & non-usable fields | Close
R7 | 2016-09-17 17:35 | Restriction of case view for client login | Close
R8 | 2016-09-20 12:49 | Cases to be archived - India | Close
R9 | 2016-10-06 14:07 | Images required | Close
R10 | 2016-11-28 14:42 | Dubai image size to be changed | Close
R11 | 2017-03-30 17:35 | Employee rate upload | Close
R12 | 2017-04-13 17:57 | New Module - Client Details | Close
R13 | 2017-04-17 17:24 | Cases to be done send to client from back end | Close
R14 | 2017-04-17 17:26 | Centerwise TAT | Close
R15 | 2017-05-08 16:25 | Archive case data | Close
R16 | 2017-06-02 15:44 | Auto refresh menu for client | Close
R17 | 2017-06-02 17:54 | Home menu to be hidden | Close
R18 | 2017-06-02 18:26 | Custom reports - heading editable | Close
R19 | 2017-06-03 13:42 | Move archive and deleted cases' images to cold storage | Close
R20 | 2017-06-08 14:16 | Images required - Dubai | Close
R21 | 2017-07-27 15:20 | Idle session timeout web - 10 mins | Close
R22 | 2018-01-29 14:48 | FE payout summary | Close
R23 | 2018-01-30 15:05 | Create Export/Import Module for All Master | Close
R24 | 2018-02-02 16:56 | Ganesh Sawant - Case data update & attachment download | Close
R25 | 2018-02-21 17:02 | Applicant document upload | Close
R26 | 2018-03-20 17:28 | Every user should change password after three month | Close
R27 | 2018-03-20 17:51 | Multiple Pincode entry in Emp Rate and Client Rate Master | Close
R28 | 2018-05-02 11:57 | Import the data of Employee Rate and Pincode. | Close
R29 | 2018-05-09 15:55 | Image upload using excel sheet path | Close
R30 | 2018-05-16 12:14 | Pincode and FE payouts | Close
R31 | 2018-06-11 14:08 | High | Close
R32 | 2018-06-13 09:24 | server customization (PHP, Mysql) | Close
R33 | 2018-06-18 12:58 | Pincode valudation at the time of upload | Close
R34 | 2018-07-06 16:46 | Move employee rates | Close
R35 | 2018-07-20 13:06 | Add Dynamic height and width for thumbnail in PDF | Close
R36 | 2018-08-01 18:28 | Deactivate DCR Activity | Close
R37 | 2018-08-20 17:13 | Mandate FE assignment | Close
R38 | 2018-08-21 14:59 | Static Map Creation | Close
R39 | 2018-08-30 12:46 | Changes in template & pdf | Close
R40 | 2018-10-03 11:01 | Client API for LTFS | Close
R41 | 2018-10-31 15:08 | Resizing image of cases | Close
R42 | 2018-11-21 17:52 | Daily MIS | Close
R43 | 2018-11-29 17:52 | import module | Close
R44 | 2018-12-05 17:22 | Upload BOCL case's reate | Close
R45 | 2018-12-13 11:39 | Change report | Close
R46 | 2019-01-24 14:11 | Password policy document | Close
R47 | 2019-02-11 13:34 | Changes in pdf design- Dubai | Close
R48 | 2019-03-18 11:46 | Add fields in template design- Dubai | Close
R49 | 2019-03-18 12:15 | Add signature in pdf design | Close
R50 | 2019-03-19 13:51 | Decrease space between table- Dubai | Close
R51 | 2019-04-01 17:08 | Dipika Yedge - Duplicate case check module | Close
R52 | 2019-05-04 13:26 | Require images | Close
R53 | 2019-05-06 09:45 | Restore case | Close
R54 | 2019-05-10 12:26 | Bulk Import | Close
R55 | 2019-05-14 12:26 | Server settings for php | Close
R56 | 2019-05-16 10:43 | Require images | Close
R57 | 2019-05-24 17:48 | Require images | Close
R58 | 2019-05-29 10:01 | Require images | Close
R59 | 2019-06-25 11:52 | Khamroddin Shaikh - QC Detail MIS | Close
R60 | 2019-06-26 11:43 | Dipika Yedge - Restore case | Close
R61 | 2019-06-27 15:47 | Khamroddin Shaikh - Create report | Close
R62 | 2019-06-29 11:09 | Dipika Yedge - Data Range to be reflected in the report | Close
R63 | 2019-07-03 15:14 | Dipika Yedge - Import FE Payout | Close
R64 | 2019-07-04 12:03 | Manas Dasgupta - Update product | Close
R65 | 2019-07-10 13:15 | Old pending cases | Close
R66 | 2019-07-10 15:11 | Dipika Yedge - YAP API | Close
R67 | 2019-07-10 15:20 | Ganesh Sawant - JPG file upload | Close
R68 | 2019-07-15 13:28 | Dipika Yedge - Change Verification Type | Close
R69 | 2019-07-23 09:47 | Dipika Yedge - Restore case | Close
R70 | 2019-08-01 16:03 | Dipika Yedge - PDF assignment | Close
R71 | 2019-08-16 15:51 | Bhavana Pachpande - Export Excel Report | Close
R72 | 2019-08-17 15:24 | Dipika Yedge - PD Billing/Payout MIS | Close
R73 | 2019-08-19 12:21 | Super Admin - Client Billing Summary | Close
R74 | 2019-08-19 12:26 | Dipika Yedge - Data storage | Close
R75 | 2019-08-19 16:32 | Dipika Yedge - EBC Data | Close
R76 | 2019-08-29 12:03 | Jayant Singh - Date wise FE & Supervisor remarks | Close
R77 | 2019-08-29 13:29 | Dipika Yedge - Verifier remarks | Close
R78 | 2019-09-05 12:20 | Dipika Yedge - Delete attached cases | Close
R79 | 2019-09-10 12:05 | Dipika Yedge - Add FE Rate 0 | Close
R80 | 2019-09-20 17:36 | Dipika Yedge - Update pincode | Close
R81 | 2019-09-21 17:27 | Manas Dasgupta - FE Payout | Close
R82 | 2019-10-09 18:26 | Dipika Yedge - Change Status | Close
R83 | 2019-11-06 12:09 | Dipika Yedge - Changes in background sevices ( FCM ) | Close
R84 | 2019-11-06 12:21 | Dipika Yedge - Add Export option | Close
R85 | 2019-11-08 16:45 | Dipika Yedge - DCR - Dashboard | Close
R86 | 2019-11-11 12:32 | Bhavana Pachpande - Date Range to be reflected in the report | Close
R87 | 2019-11-13 13:52 | Dipika Yedge - Employee Type | Close
R88 | 2019-11-14 16:47 | Ganesh Sawant - Client Details and Masters | Close
R89 | 2019-11-18 13:34 | Dipika Yedge - New field in Employee Master | Close
R90 | 2019-11-25 11:48 | Dipika Yedge - Delete PD Employee Rates | Close
R91 | 2019-12-20 16:24 | Dipika Yedge - Send to client | Close
R92 | 2019-12-20 16:45 | Dipika Yedge - Add xls format | Close
R93 | 2020-01-03 18:32 | Dipika Yedge - FE Rate Deletion | Close
R94 | 2020-01-28 14:40 | Bhavana Pachpande - Reopen- Paid cases | Close
R95 | 2020-01-28 14:59 | Super Admin - Stop Check | Close
R96 | 2020-02-18 12:30 | Dipika Yedge - TAT Calculation | Close
R97 | 2020-02-18 12:39 | (All Members) - New Master Page | Close
R98 | 2020-02-27 14:35 | Dipika Yedge - direct sent to client | Close
R99 | 2020-03-04 15:02 | Super Admin - P flag in DCR_Appt Billing MIS | Close
R100 | 2020-05-02 11:26 | Kailash Kumawat - Lat long for web | Close
R101 | 2020-08-06 22:29 | Ajit Kedare - API requirement KVB | Close
R102 | 2020-09-18 15:32 | Dipika Yedge - Address on RES images | Close
R103 | 2020-12-08 11:22 | Dipika Yedge - Export option for Sub Menu List | Close
R104 | 2020-12-08 15:30 | Bhavana Pachpande - Master for EBC | Close
R105 | 2021-06-30 12:15 | Bhavana Pachpande - Summary page in disclaimer end of report | Close
R106 | 2021-07-15 18:09 | Dipika Yedge - Summary page sequence and import sequence | Close
R107 | 2021-07-29 11:12 | Bhavana Pachpande - Required employee code in pdf design | Close
R108 | 2021-08-02 13:37 | Bhavana Pachpande - The import sequence and the summary sequence should be the same | Close
R109 | 2021-10-20 18:34 | Bhavana Pachpande - Separate URL for HDFC Liability | Close
R110 | 2021-10-28 17:09 | Dipika Yedge - Standard Remarks | Close
R111 | 2021-11-15 16:59 | Ganesh Sawant - Unable to extract the report in Google chrome | Close
R112 | 2021-11-15 17:01 | (All Members) - Data shifting from online to cold server | Close
R113 | 2021-12-13 17:21 | Dipika Yedge - Export is required to Client Details list | Close
R114 | 2021-12-30 16:40 | Dipika Yedge - Employee Rate | Close
R115 | 2022-01-06 15:30 | Bhavana Pachpande - Case verification page | Close
R116 | 2022-05-20 12:26 | Bhavana Pachpande - Biiling Format- Dubai | Close
R117 | 2022-07-01 14:58 | (All Members) - Vertical wise tenure of the data storage | Close
R118 | 2022-09-12 15:42 | Dipika Yedge - Axis MAB report | Close
R119 | 2022-12-20 11:40 | (All Members) - PMS Software - Path Forward | Hold
R120 | 2023-01-07 17:51 | (All Members) - Import old cases using excel | Close
R121 | 2023-01-20 15:41 | Dipika Yedge - Radio field type options | Close
R122 | 2023-01-23 16:00 | (All Members) - Archieve Manually | Close
R123 | 2023-01-31 12:49 | (All Members) - AWS India Check List | Open
R124 | 2023-02-07 15:11 | Dipika Yedge - HDFC-KYC | Close
R125 | 2023-02-24 13:23 | Dipika Yedge - Import option for Bank URL | Open
R126 | 2023-03-10 12:08 | Ramakrishnan V - Auto inactive user in the RES if no any activity done in the last 30 days | Open
R127 | 2023-03-10 14:26 | Dharmendrakumar Vishwakarma - Active user to be deactivated basis of the DOL pass in through the EasyHR API | Open
R128 | 2023-03-10 19:19 | (All Members) - Required Option to upload HDFC Bank Limited KYC manual and same should be accessible to inputter and authorizer | Close
R129 | 2023-03-24 13:58 | (All Members) - Forget password function | Close
R130 | 2023-04-01 13:26 | (All Members) - Request to share the RES Server report every after 2 hours | Close
R131 | 2023-04-08 12:58 | Dipika Yedge - Archive for table case history | Open
R132 | 2023-04-08 16:59 | (All Members) - New Summary Format for RCU | Close
R133 | 2023-04-25 16:39 | (All Members) - Bank Statement wise FE rate | Close
R134 | 2023-04-26 17:11 | Ramakrishnan V - Required Auto logout to be set for the INDIA | Open
R135 | 2023-05-24 16:09 | (All Members) - Tables without ny date field like created date/ entry date / or modified date etc | Close
R136 | 2023-06-07 15:46 | Dipika Yedge - Dubai- New FE wise MIS | Open
R137 | 2023-06-30 16:26 | Ramakrishnan V - Image compress size to be increase for the clarity | Open
R138 | 2023-08-29 15:29 | (All Members) - Cases Not show in Mobile Application | Close
R139 | 2023-10-09 12:58 | Dharmendrakumar Vishwakarma - reload not require in FE Assignment menu | Open
R140 | 2023-10-09 17:18 | Manas Dasgupta - Login multiple device | Open
R141 | 2023-10-09 17:35 | Dipika Yedge - Close case status update send to mobile | Open
R142 | 2023-10-19 15:17 | (All Members) - Dubai- FE Status MIS | Close
Showing 1 to 142 of 142 entries
Previous
1
Next